**Daily Scrum Meeting Report**

**Sprint 1**

Scrum Master : Tiang Wei Seong

Sprint Date : 6-11-2016 till 25-11-2016

Sprint Duration : 16 days

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Day | Date | Planning | Task Accomplish | Problems |
| 1 | 6-11-2016 | Discussion with the client what requirement ,sources and services needed in the system. | None | None |
| 2 | 7-11-2016 | Planning for the initial system requirement with the developers. | A list of system requirement , sources and services of the system needed in Sprint 1. | Difficulty on investigate and determine the feasibility of request. |
| 3 | 8-11-2016 | Discussion of the modules, classes, and databases needed in the system. | Classes, database and entities has been designed. | Difficulty on deciding the entity needed for all the classes. |
| 4 | 9-11-2016 | Declare the relationship between the classes and modules in the system. | DFD, ERD model for the flow of the system processes has been defined. | Difficulty on designed the relationship between each modules and classes of entities. |
| 5 | 10-11-2016 | Discussion of the design of system user interface for each module that has been declare. | Designed the user interface of each modules defined in Sprint 1. | None |
| 6 | 11-11-2016 | Discussion with the client of all the design of the system has reached their requirements. | Received client’s feedback for the system requirements. | None |
| 7 | 14-11-2016 | Improves the user interface with the additional requirements from the client’s feedback. | The user requirements has been changed. | None |
| 8 | 15-11-2016 | Finalize the requirement for the system design and start to design. | System design has been finalised in Sprint 1 of all module | None |
| 9 | 16-11-2016 | Coding Implementing for the staff login modules in the system | None | None |
| 10 | 17-11-2016 | Coding Implementing for the reservation, schedule,bus and route modules | Staff Login modules was done. | Difficulty on designed the route and bus schedule which need to comes along with the reservtion modules. |
| 11 | 18-11-2016 | Coding Implementing for the payment and ticket modules | Reservation, Bus schedule, Bus and route modules was done. | None |
| 12 | 21-11-2016 | Validation for all the input fields for all the modules in Sprint 1. | Payment and print ticket modules was done. | The data type for entities might wrongly declared. |
| 13 | 22-11-2016 | Implementing database in Sprint 1 and fixing the data type error. | All the data input field has been successfully implemented. | Difficulty on linking the primary key and foreign key. |
| 14 | 23-11-2016 | Finalise all the module is in the system requirement in Sprint 1. | Database was implemented successfully for all the modules in Sprint 1. | None |
| 15 | 24-11-2016 | Implement testing for all the modules in the system. | System has been finalized | None |
| 16 | 25-11-2016 | Fixed the bugs and error in all modules in the system. | System has been tested completely by solving all the bugs and error. | Bugs and Errors |